# Metrics Definitions — Renewal Portfolio

Keolis Valmont · governed measures v1.0 · 15 September 2026 · owner: Amélie Roussel (investment controller)

Every measure has a named owner, a business definition, a grain, inclusion rules, a date basis, a currency and a version. Money is EUR HT at the posting date. Forecast rounds are R1 (April), R2 (July) and R3 (October).

## 1. Forecast Total Project Cost

Forecast Total Project Cost is the headline figure of the monthly investment review and the number the authority's quarterly PPI review is judged against.

Definition. Posted actuals plus valid uninvoiced accruals plus the forecast cost to complete, per project, EUR HT.

Used for. The monthly investment review and the quarterly PPI review.

How it is calculated. Accruals are reversed when the invoice arrives; the cost to complete excludes anything already accrued, so nothing is counted twice.

Answers. “Which renewal projects are forecasting above their approved budget, and by how much?”

SELECT p.project_code,

SUM(t.amount_eur) + COALESCE(a.accrued, 0) + f.ctc_committed_eur + f.ctc_uncommitted_eur + f.contingency_eur AS forecast_total_eur

FROM `ppm`.`project` p

JOIN `fin`.`cost_transaction` t ON t.project_code = p.project_code

LEFT JOIN (SELECT project_code, SUM(amount_eur) AS accrued FROM `fin`.`accrual_line` WHERE matched_invoice IS NULL GROUP BY 1) a ON a.project_code = p.project_code

JOIN `fin`.`forecast_snapshot` f ON f.project_code = p.project_code AND f.scenario = 'Working'

GROUP BY p.project_code, a.accrued, f.ctc_committed_eur, f.ctc_uncommitted_eur, f.contingency_eur;

## 2. Operator Exposure

Operator Exposure is what the Directrice générale reports to Keolis France — the part of the renewal programme Keolis Valmont itself bears.

Definition. Costs borne by Keolis Valmont under validated allocations: GER projects in the contract price plus its share of co-funded projects; unresolved exposure shown as a separate scenario.

Used for. The Keolis France investment committee.

How it is calculated. Never equal to project cost: an authority-funded renewal is not operator exposure, and a disputed recovery is not counted as certain.

Answers. “What is Keolis Valmont's own exposure on the renewal portfolio, separate from the authority's?”

SELECT p.project_code, b.funding_source, SUM(b.amount_eur) AS approved_eur

FROM `ppm`.`project` p

JOIN `fin`.`budget_line` b ON b.project_code = p.project_code

WHERE b.funding_source IN ('GER')

GROUP BY 1, 2;

## 3. Service Availability Margin

Service Availability Margin is checked before any vehicle withdrawal or track closure is approved.

Definition. Eligible available vehicles minus the peak requirement minus the agreed reserve, by vehicle class and day type.

Used for. Service planning and the weekly readiness call.

How it is calculated. Each unavailable vehicle is subtracted once, from its availability interval — an open work order alone does not make a vehicle unavailable.

Answers. “Do we have enough vehicles for peak service while assets are withdrawn for renewal?”

SELECT r.vehicle_class, r.day_type, r.peak_required, r.reserve_required

FROM `ops`.`service_requirement` r

WHERE r.timetable_version = 'HIV-2026';

## 4. Schedule Variance

Schedule Variance is the first thing the weekly project review looks at.

Definition. Current forecast milestone date minus the approved baseline milestone date, in working days.

Used for. The weekly project review.

How it is calculated. An approved re-baseline is shown as such; a supplier's new date in an email is not a schedule change until the project office records it.

Answers. “Which milestones have slipped against their approved baseline?”

SELECT s.project_code, s.task_name, s.baseline_finish, s.current_finish,

DATE_DIFF(s.current_finish, s.baseline_finish, DAY) AS variance_days

FROM `ppm`.`schedule_task` s

WHERE s.current_finish > s.baseline_finish;

## 5. Documented Acceptance Completeness

Documented Acceptance Completeness decides whether a campaign can be reported as complete to the authority.

Definition. Verified required acceptance items divided by applicable required items, per project.

Used for. Handover and the PPI claim evidence pack.

How it is calculated. Completeness is not permission to operate; release for duty is issued separately by operations.

Answers. “Which campaigns are installed but not yet accepted?”

SELECT a.project_code, COUNTIF(a.result = 'Passed') / COUNT(*) AS completeness

FROM `ppm`.`acceptance_item` a

GROUP BY a.project_code;

## 6. Renewal Backlog

Renewal Backlog is presented to the authority at each quarterly PPI review.

Definition. Validated intervention needs not yet completed, by status: unfunded, option study, deferred, approved.

Used for. The quarterly PPI review and the annual renewal programme.

How it is calculated. Overlapping options for the same need are counted once; safety and mandatory needs are flagged and cannot be traded away by a score.

Answers. “Which assets must be renewed, and which needs are still unfunded?”

SELECT n.status, COUNT(*) AS needs, SUM(n.estimate_eur) AS estimate_eur

FROM `ppm`.`intervention_need` n

WHERE n.status <> 'Approved'

GROUP BY n.status;

## 7. Approved Funding Gap

Approved Funding Gap is escalated to the authority when it exceeds €250,000 on a project.

Definition. Forecast fundable expenditure minus applicable approved funding, per PPI project.

Used for. The quarterly PPI review.

How it is calculated. Scope, caps and co-funding rules apply; costs the convention does not cover are labelled separately rather than netted.

Answers. “Where does the forecast exceed the funding the authority has approved?”

SELECT f.project_code, SUM(f.ctc_committed_eur + f.ctc_uncommitted_eur) AS remaining_eur

FROM `fin`.`forecast_snapshot` f

WHERE f.scenario = 'Working'

GROUP BY 1;

## 8. Failure Frequency

Failure Frequency is how the maintenance team argues for renewal ahead of the contractual replacement date.

Definition. Relevant heavy-component failures per 100,000 km, by vehicle series.

Used for. The annual renewal programme.

How it is calculated. Months with a meter reset are excluded; the peer group is the same vehicle class.

Answers. “Which vehicle series fail most often, per kilometre run?”

SELECT a.model, COUNT(f.failure_id) / (SUM(u.distance_km) / 100000) AS failures_per_100k_km

FROM `eam`.`failure_event` f

JOIN `eam`.`asset_register` a ON a.asset_id = f.asset_id

JOIN `eam`.`usage_monthly` u ON u.asset_id = f.asset_id AND u.meter_reset_flag = FALSE

GROUP BY a.model;

## 9. Open Commitment

Open Commitment is reconciled with procurement at every month-end close.

Definition. Ordered value less received and cancelled value, per PO line, at the line's valuation basis.

Used for. The month-end close.

How it is calculated. Unpaid invoices are not future work; a supplier's revised promise does not change the commitment.

Answers. “How much is committed on each project but not yet received?”

SELECT l.project_code, SUM(l.ordered_eur - l.received_eur - l.cancelled_eur) AS open_commitment_eur

FROM `proc`.`po_line` l

GROUP BY 1;

Hypothetical demonstration document. Keolis Valmont, Valmont Métropole, the contract and every figure are fictional.